## Cover
QA Test Plan
for RASAI
Client Maintenance
QA TEST PLAN
TABLE OF CONTENTS
INTRODUCTION 1
OBJECTIVES 1
SPRINT OVERVIEW 1
ROLES AND RESPONSIBILITIES 1
TEST STRATEGY 1
TEST DELIVERABLES 1
TEST SCENARIOS 1
TEST CASES 1
TEST EXECUTION 1
DEFECT MANAGEMENT 1
TEST REPORTING 1
CLOSURE CRITERIA 1
APENDICES 1

## QA Test Plan
INTRODUCTION
The purpose of this test plan is to ensure the quality of features developed during Sprint 1 and Sprint 2 of RASAI project.
The scope includes testing of Client Maintenance functionalities, About Page, Login/Logout Page, and Booking Page.
Key stakeholders: Project Manager, Product Owner, Development Team, Tester, Database.
OBJECTIVES
Validate the functionality client maintenance, About Page, Admin page and Booking page.
Criteria for success: All critical and high-priority test cases pass with no critical defects open at the end of the sprints.
SPRINT OVERVIEW
Sprint Dates: [11/4/2024] to [6/6/2024]
Sprint Goals: Implement Client Maintenance and Bookings.
Features: About Page, Login/Logout Page and Booking Page.
ROLES AND RESPONSIBILITIES
Testing: Tester
Responsibilities: Testers - Test case execution, defect reporting.
TEST STRATEGY
Agile Testing Approach
Functional Testing
Automation using Selenium.
Test Environments: Development.
TEST DELIVERABLES
Test Cases: Refer to About/Bookings/Admin Tabs
TEST SCENARIOS
About:
Verify About page download successfully, layout is correct.
Verify responsiveness of the page.
User Registration Login/Logout:
Verify successful registration with valid credentials.
Verify error messages for invalid inputs.
TEST CASES
Detailed test cases available in the Test Cases document.
TEST EXECUTION
Test Execution Schedule: [Final Testing 15/6/2024]
Test Execution Environment Setup: Ensure test environments are aligned with development environments.
Execution Progress Tracking: Daily stand-up meetings.
DEFECT MANAGEMENT
Defect Severity: Critical, Major, Minor.
Defect Priority: High, Medium, Low.
TEST REPORTING
Daily Status Reports: Test progress, issues, and risks.
Sprint Summary Reports: Test results summary, defect metrics.
CLOSURE CRITERIA
All critical and high-priority test cases pass.
No critical defects open.
Test report reviewed and approved by stakeholders.
APPENDICES
References: Project Plan, Requirements, Design Documents, Sprint Planning,Agendas.

## HomePage
Sprint Test Plan
Project Name | Rasai
Test Plan Completion Date | 2024-06-15
Created By | Gagandeep Kaur
Date | Sr. No. | Test Case Name | Priority | Home Page | Test Steps | Expected Result | Actual result | Severity | Time to Execute | Status | Test Page | Comments
2024-05-15 | 1 | Home Page | High | Loading of Home Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the Rasai LOGO on the top Left hand side. | By default home page should load successfully when opened the webpage. Clicking on Logo should also load Home page . | No Information is showing on the Home Page. | Major | 2.4sec | Fail |  | Blank Page is showing, no information about the Home Page.
2024-06-08 | 1 | Home Page | High | Loading of Home Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. | By default home page should load successfully when opened the webpage. Clicking on Logo should also load Home page . | Image is Overlapping on the Navigation Bar and User won't be able to see About and Menu Page from the navigation Bar. | Major | 2.4sec | Fail | MainPage Test | User won't be able to see About and Menu Pages from the Navigation Bar.
2024-06-08 | 2 | Home Page > Navigation Bar> Booking | Medium | Loading of Home Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. Click on Booking link in navigation bar | Booking page should load successfully . | Booking Page Loaded Properly |  |  | Pass
2024-06-08 | 3 | Home Page > Navigation Bar> Login | Medium | Loading of Home Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. | Login Page should load successfully. | Login Page Loaded Properly |  |  | Pass
2024-06-08 | 4 | Home Page > About Page | Medium | Loading of Home Page | 1. Open Chrome browser. Click on the About link of from the Home Page. | About page should load successfully . | Webpage should load properly. | Minor | 2.4sec | Fail | MainPage Test | Webpage is loading but there is a space around the images which is not looking properly and images are not aligned with the text.
2024-06-08 | 5 | Home Page > Menu Page | Medium | Loading of Home Page | 1. Open Chrome browser. Click on the Menu link of from the Home Page. | Menu page should load successfully . | Webpage should load properly. |  | 2.4sec | Pass
2024-06-08 | 6 | Home Page > Booking Page | Medium | Loading of Home Page | 1. Open Chrome browser. Click on the Booking link of from the Home Page. | Booking page should load successfully . | Webpage should load properly. |  | 2.4sec | Pass
2024-06-08 | 7 | Home Page > Footer>About Page | Medium | Loading of Home Page | 1. Open Chrome browser. Click on the About link of from footer. | About page should load successfully . | Webpage should load properly. | Minor | 2.4sec | Fail |  | Webpage is loading but there is a space around the images which is not looking properly and images are not aligned with the text.
2024-06-08 | 8 | Home Page > Footer>Menu Page | Medium | Loading of Home Page | 1. Open Chrome browser. Click on the Menu link of from footer. | Menu page should load successfully . | Webpage should load properly. |  | 2.4sec | Pass
2024-06-08 | 9 | Home Page > Footer>Booking Page | Medium | Loading of Home Page | 1. Open Chrome browser. Click on the Booking link of from footer. | Booking page should load successfully . | Webpage should load properly. |  | 2.4sec | Pass
2024-06-15 | 1 | Home Page |  | Loading of Home Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. | By default home page should load successfully when opened the webpage. Clicking on Logo should also load Home page . | Able to see the navigation bar properly. |  |  | Pass | MainPage Test
2024-06-15 | 2 | Home Page > Navigation Bar > About Page | Medium | Loading of About Page | 1. Open Chrome browser. Click on the About link of from the navigation bar. | About page should load successfully . | Webpage loaded properly. | Minor | 2.4sec | Fail | MainPage Test | Webpage is loading but there is a space around the images which is not looking good and images are not aligned with the text. Also need to find the white box popping to click the box which is not user friendly.
2024-06-15 | 3 | Home Page > Navigation Bar > Menu Page | Medium | Loading of Menu Page | 1. Open Chrome browser. Click on the Menu link of from the Home Page. | Menu page should load successfully . | Webpage not loaded properly. | Major |  | Fail | MainPage Test | Error page is showing
2024-06-15 | 4 | Home Page > Navigation Bar> Booking | Medium | Loading of Booking Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. Click on Booking link in navigation bar | Booking page should load successfully . | Booking Page Loaded Properly | Minor |  | Fail | MainPage Test | Need to find the white box popping to click the box which is not user friendly.
2024-06-15 | 5 | Home Page > Navigation Bar> Login | Medium | Loading of Login Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. | Login Page should load successfully. | Login Page Loaded Properly | Minor |  | Fail | MainPage Test | Need to find the white box popping to click the box which is not user friendly.
2024-06-15 | 6 | Home Page | High | Loading of Menu Page | 1. Click on " Visit our Menu!" button. | Clicking on the visit our menu button should also load menu page . | Error page showing | Major | 2.4sec | Fail | MainPage Test | Error page is showing
2024-06-15 | 7 | Home Page > About Page | Medium | Loading of About Page | 1. Open Chrome browser. Click on the About link on the home page. | About page should load successfully . | Webpage should load properly. | Minor | 2.4sec | Fail | MainPage Test | Webpage is loading but there is a space around the images which is not looking properly and images are not aligned with the text.
2024-06-15 | 8 | Home Page > Menu Page | High | Loading of Menu Page | 1. Open Chrome browser. Click on the Menu link of from the Home Page. | Menu page should load successfully . | Webpage should load properly. | Major |  | Fail | MainPage Test | Error page is showing
2024-06-15 | 9 | Home Page > Booking |  | Loading of Booking Page | 1. Open Chrome browser. Click on Booking link from the home page | Booking page should load successfully . | Booking Page Loaded Properly |  |  | Pass | MainPage Test
2024-06-15 | 10 | Home Page > Footer>About Page | Medium | Loading of Home Page | 1. Open Chrome browser. Click on the About link of from footer. | About page should load successfully . | Webpage should load properly. | Minor | 2.4sec | Fail | MainPage Test | Webpage is loading but there is a space around the images which is not looking properly and images are not aligned with the text.
2024-06-15 | 11 | Home Page > Footer>Menu Page | Medium | Loading of Home Page | 1. Open Chrome browser. Click on the Menu link of from footer. | Menu page should load successfully . | Webpage should load properly. |  | 2.4sec | Fail | MainPage Test | Error page is showing
2024-06-15 | 12 | Home Page > Footer>Booking Page |  | Loading of Home Page | 1. Open Chrome browser. Click on the Booking link of from footer. | Booking page should load successfully . | Webpage should load properly. |  | 2.4sec | Pass | MainPage Test

## AboutPage
Sprint Test Plan
Project Name | Rasai
Test Plan Creation Date | 2024-06-15
Created By | Gagandeep Kaur
Date | Sr. No. | Sprint1 | Test Case Name | Priority | Test Description | Test Steps | Expected Result | Actual result | Severity | Time to Execute | Status | Test Link | Comments
2024-05-15 | 1 | Sprint1 | About Page | Medium | Loading of About Page | 1.Click on the About link in the Navigation Bar | About page should load successfully. Image and Text should load successfully. | About page loaded successfully. |  | 2.6 sec | Pass
2024-05-15 | 2 | Sprint1 | About Page | Medium | Loading of About Page | 1. Minimize the window | About page should load successfully. Image and Text should load successfully. | A black text box is showing below the images which makes UI not looking good. | Minor | 2.6 sec | Fail |  | A black text box is showing below the images which makes UI not looking good.
2024-05-15 | 3 | Sprint1 | Footer >About Page | Medium | Loading of About Page | 1. Click on the About link in the Footer. 2. Maximize the window | About page should load successfully. Image and Text should load successfully. | Maximize the window, page is loading successfully. |  | 2.6 sec | Pass
2024-05-15 | 4 | Sprint1 | Footer >About Page | Medium | Loading of About Page | 1. Click on the About link in the Footer . 2. Minimize the window | About page should load successfully. Image and Text should load successfully. | A black text box is showing below the images which makes UI not looking good. | Minor | 2.6 sec | Fail |  | A black text box is showing below the images which makes UI not looking good.
2024-05-15 | 5 | Sprint1 | About Page | Medium | Responsiveness of About Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Navigation Bar is not showing properly. | Website should load successfully in the Mobile Version. | Navigation Bar is not showing properly in mobile version. | Minor | 2.6 sec | Fail |  | Better to have a Toggle bar.
2024-05-15 | 6 | Sprint1 | About Page | Medium | Responsiveness of About Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the About link in the Navigation Bar | About page should load successfully. Image and Text should load successfully in the Mobile Version. | Webpage is not loading properly in mobile version. Black box is showing in below the images. Text is also not showing properly. | Major | 2.6 sec | Fail |  | Webpage is not loading properly in mobile version. Black box is showing in below the images. Text is also not showing properly.
2024-05-15 | 7 | Sprint1 | About Page | Medium | Responsiveness of About Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the About link from the footer | About page should load successfully. Image and Text should load successfully in the Mobile Version. | Webpage is not loading properly in mobile version. Black box is showing in below the images. Text is also not showing properly. | Major | 2.6 sec | Fail |  | Webpage is not loading properly in mobile version. Black box is showing in below the images. Text is also not showing properly.
2024-05-15 | 9 | Sprint1 | About Page | Medium | Responsiveness of About Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the About link from Navbar or Footer. 3. Images should load properly. | About page should load successfully. Image and Text should load successfully in the Mobile Version. | Webpage is not loading properly in mobile version. Images on the About page is not looking properly. One image is going right to the text and another is going out of the screen. | Major | 2.6 sec | Fail |  | Images on the About page not showing properly.
2024-06-08 | 10 | Sprint1 | About Page |  | Loading of About Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the About link on Home Page/Main Page | About page should load successfully. Image and Text should load successfully and shown correctly. | Webpage is loading but there is a space around the images which is not looking properly and images are not aligned with the text. | Minor |  | Fail |  | Space around the images and images are not aligned with the text properly.
2024-06-08 | 11 | Sprint1 | About Page |  | Responsiveness of About Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the About link from Home Page 3. Images should load properly. | About page should load successfully. Image and Text should load successfully in the Mobile Version. | Webpage is not loading properly in mobile version. Images on the About page is not looking properly. Text is Overlapping. There is a white space next to the image | Major |  | Fail |  | Text is Overlapping. Space is showing next to the image
2024-06-08 | 12 | Sprint1 | About Page | Medium | Responsiveness of About Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. | Website should load successfully in the Mobile Version. | Toggle bar is showing |  | 2.6 sec | Pass |  | Toggle bar is showing
2024-06-15 | 2 | Sprint1 | About Page | Medium | Responsiveness of About Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the About link from Home Page | About page should load successfully. | Webpage is not loading properly in mobile version. Images on the About page is not looking properly. Text is Overlapping. There is a white space next to the image. | Major |  | Fail |  | Text is Overlapping. Space is showing next to the image
2024-06-15 | 3 | Sprint1 | About Page | High | Responsiveness of About Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the About link from Home Page 3. Images should load properly. | About Page should load successfully in the Mobile Version. | Logo is showing in the middle, no navigation bar is showing. | Major | 2.6 sec | Fail |  | Toggle bar is not showing

## Sprint2-Bookings
Sprint Test Plan
Project Name | Rasai
Test Plan Creation Date | 2024-06-15
Created By | Gagandeep Kaur
Date | Sprint2 | Module | Test Case Name | Priority | Test Description | Test Steps | Expected Result | Severity | Time to Execute | Status | Test Link | Comments
2024-06-15 | Sprint2 | Bookings | Booking Page |  | Loading of BookingPage | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the Booking link in the Navigation Bar | Booking page should load successfully.All the fields should display properly. |  |  | Pass |  | Booking Page is loading successfully
2024-06-15 | Sprint2 | Bookings | Booking Page |  | First Name Field | 1. Click on the Bookings tab in the navigation bar. 2. Enter first name field . | User should be able to click on the bookings tab and able to enter his/her first name in the field. |  |  | Pass
2024-06-15 | Sprint2 | Bookings | Booking Page |  | Last Name Field | 1. Click on the Bookings tab in the navigation bar. 2. Enter Last name field . | User should be able to click on the bookings tab and able to enter his/her last name in the field. |  |  | Pass
2024-06-15 | Sprint2 | Bookings | Booking Page |  | Email | 1. Click on the Bookings tab in the navigation bar. 2. Enter valid emailfield . | User should be able to click on the bookings tab and able to enter his/her valid email id in the field. |  |  | Pass
2024-06-15 | Sprint2 | Bookings | Booking Page | High | Email | 1. Click on the Bookings tab in the navigation bar. 2. Enter invalid emailfield . | Error message or pop up message should be displayed with entered invalid email id. | Major |  | Fail |  | No Validation error message is showing.
2024-06-15 | Sprint2 | Bookings | Booking Page |  | Phone no. | 1. Click on the Bookings tab in the navigation bar. 2. Enter valid phone no. | User should be able to click on the bookings tab and able to enter his/her valid phone no. in the field. |  |  | Pass
2024-06-15 | Sprint2 | Bookings | Booking Page | High | Phone no. | 1. Click on the Bookings tab in the navigation bar. 2. Enter invalid phone no. | Error message or pop up message should be displayed with entered invalid phone no. | Major |  | Fail |  | Able to put alphabets, no validation
2024-06-15 | Sprint2 | Bookings | Booking Page | High | EventDate/Time | 1. Click on the Bookings tab in the navigation bar. 2. Enter event date/time. | User should be able to click on the bookings tab and able to enter his/her valid date/time in the field. | Major |  | Fail |  | Able to put alphabets, no validation
2024-06-15 | Sprint2 | Bookings | Booking Page | High | No. Of Adults/Children | 1. Click on the Bookings tab in the navigation bar. 2. Enter no. of adults/children. | User should be able to click on the bookings tab and able to enter no. of adults and no. of children field. | Major |  | Fail |  | Able to put alphabets, no validation
2024-06-15 | Sprint2 | Bookings | Booking Page |  | Special Request | 1. Click on the Bookings tab in the navigation bar. 2. Enter any special requests. | User should be able to click on the bookings tab and able to enter any special request in the field provided. |  |  | Pass
2024-06-15 | Sprint2 | Bookings | Booking Page | High | Send Button | 1. Click on the send button after filling all the fields. | User should be able to book the event successfully. | Major |  | Fail |  | It’s a static page
2024-06-15 | Sprint2 | Bookings | Booking Page |  | Loading of BookingPage | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the Booking link from footer | Booking page should load successfully.All the fields should display properly. |  |  | Pass
2024-06-15 | Sprint2 | Bookings | Booking Page | High | Responsiveness of Booking Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the Booking link in the Navigation Bar | Booking page should load successfully. Image and Text should load successfully in the Mobile Version. | Major |  | Fail |  | Not showing properly.

## Sprint1-AdminPage
Sprint Test Plan
Project Name | Rasai
Test Plan Creation Date | 2024-06-15
Created By | Gagandeep Kaur
Date | Sr. No. | Sprint1 | Test Case Name | Priority | Test Description | Test Steps | Expected Result | Actual result | Severity | Time to Execute | Status | Comments
2024-06-15 | 1 | Sprint1 | Login Page | Medium | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar | Admin page should load successfully. Admin should be able to view orders/bookings and maintain customers and other web elements.
2024-06-15 | 2 | Sprint1 | Login Page | Medium | Loading of Admin Page | 1. Minimize the window | Admin page should load successfully. | Admin page loaded successfully.
2024-06-15 | 3 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on Create Item | Create menu item page loaded successfully. | Create menu items page loaded successfully.
2024-06-15 | 4 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on Create Item 3. Enter Name Field. | Admin should be able to enter text in name field | Able to enter name successfully |  |  | Pass | Able to enter name successfully
2024-06-15 | 5 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on Create Item 3. Enter Description Field. | Admin should be able to enter text in description field | Able to enter description successfully |  |  | Pass | Able to enter description successfully
2024-06-15 | 6 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on Create Item 3. Enter valid Price in Price Field. | Admin should be able to enter valid price. | Able to enter price successfully |  |  | Pass | Able to enter price successfully
2024-06-15 | 7 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on Create Item 3. Enter invalid Price in Price Field. | Error message should pop up if entered invalid price. | Error message is showing |  |  | Pass | Able to see the error message.
2024-06-15 | 8 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on Create Item 3. Enter valid ImageURL Field. | Admin should be able to enter valid image URL. | Able to enter valid image URL. |  |  | Pass
2024-06-15 | 9 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on Create Item 3. Enter invalid ImageURL Field. | Error message should pop up if entered invalid ImageURL. | No Validation for this field. |  |  | Fail | No validation is there in this field
2024-06-15 | 10 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on View Menu Items | Menu Items page should load. | Error Page is showing. | Major |  | Fail | Error Page is showing.
2024-06-15 | 11 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on Home link on Left side of the Login page. | Home page should load successfully | Home Page should load successfully. |  |  | Pass
2024-06-15 | 12 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on Create Menu item link on Left side of the Login page. | Create menu item page should loaded successfully. | Create menu item page loaded successfully. |  |  | Pass
2024-06-15 | 13 | Sprint1 | Login Page |  | Loading of Admin Page | 1.Click on the Login link in the Navigation Bar 2. Click on Menu link on Left side of the Login page. | Menu page should load successfully | Error Page is showing. | Major |  | Fail | Error Page is showing
2024-06-15 | 14 | Sprint1 | Login Page | Medium | Responsiveness of Login Page | 1. Open Chrome browser. Open the link of the Rasai Webpage. 2. Click on the Login link in the Navigation Bar | Admin page should load successfully. All the elements of the admin page on the left hand side should display properly. | Page loaded successfully but button are overlapping on each other. | Major |  | Fail | Not showing properly.